## Sheet1
S.NO | User Stories | Tasks | Resource | Estimated Hours | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date
1 | Homepage | UI Development | Subapriya Madasamy | 35
2 | Homepage | API Development | Subapriya Madasamy | 20
3 | Login page | API Development | Manikandan | 25
4 | Login page | UI Development | Manikandan | 30
5 | Login page | Authentication and Authorization | Manikandan | 60
6 | Login page | Forgot Password | Manikandan | 40
7 | Dashboard | Listing all tickets - API Development | Subapriya Madasamy | 45
8 | Dashboard | UI Development | Subapriya Madasamy | 45
9 | AddUserStory | API Development | Monisha Selvaraj | 30
10 | AddUserStory | UI Development | Monisha Selvaraj | 30
11 | GetAllTickets | API Development | Monisha Selvaraj | 10
11 | GetTicketById | API Development | Monisha Selvaraj | 10
12 | UpdateUserStory | API Development | Monisha Selvaraj | 40
13 | UpdateUserStory | UI Development | Monisha Selvaraj | 35
14 | AddBug | API Development | Viyan Anbazhagan | 30
15 | AddBug | UI Development | Viyan Anbazhagan | 45
16 | UpdateBug | API Development | Viyan Anbazhagan | 35
17 | UpdateBug | UI Development | Viyan Anbazhagan | 45
18 | AddCustomerSupport | API Development | Dharshini Chandru | 35
19 | AddCustomerSupport | UI Development | Dharshini Chandru | 45
20 | UpdateCustomerSupport | API Development | Dharshini Chandru | 30
21 | UpdateCustomerSupport | UI Development | Dharshini Chandru | 45
22 | Filters | API Development | Subapriya Madasamy | 35
23 | Versioning | API Development | Viyan Anbazhagan and Manikandan | 50
24 | Versioning | UI Development | Monisha Selvaraj and Dharshini Chandru | 50
| Total |  |  | 900